## Cover Page
CLASSIFICATION
<Logo of Client>
<Product Name>
SYSTEM INTEGRATION TESTING (SIT)
Digital Application Standardization and Modernization Roadmap Phase 1 Implementation
<Project Name>

## MAISP
<Project Name>
Security Testing (MAISP) Acknowledgement
I hereby confirm that the system, application and/or server for this project or change request (CR) complies to Malaysia Airports
Information Security Policy (MAISP) and Generic Server Security Baseline Guidelines with the following configuration in place:
System & Application:
1 | Change of password to occur every 180 days (MAISP-050303)
2 | Password to contain a minimum of eight (12) alphanumeric character (MAISP-050302)
3 | Password to contain uppercase (ABC), lowercase (abc), numbers (0,1,2) and special characters (#$@) (MAISP-050407)
4 | The past four (04) passwords should NOT be reused (MAISP-050407)
5 | Unique user-ID and password required (MAISP-050510)
6 | Application screen lock duration: 15 mins (MAISP-070205)
Server:
1 | Account lockout duration: 30 min (5.2.2)
2 | Number of failed logon attempts allowed: 5 (5.1.3)
3 | Reset failed logon attempts count after: 30 min (5.2.2)
4 | Maximum password age (lifetime): 45 days (5.1.1)
References:
1 | Policy - Malaysia Airports Information Security Policy (MAISP) - MAHB/HDQ/POL/ITD/01
2 | Guidelines - Generic Server Security Baseline - MAHB/HDQ/GL/ITD/25

## Sign-Off
<Project Name>
SYSTEM INTEGRATION TESTING (SIT) Signature Acknowledgement
Demonstrated By: |  | Demonstrated By: | Witnessed By: | Witnessed By:
Witnessed By: |  | Witnessed By: | Tested By: | Approved By:

## TRD
TECHNICAL REQUIREMENT DOCUMENT
Project Title
BR# | Module Name | Applicable Roles | Description
Web
B1 | Login | Valid User(s) | Only valid user(s) can access this module.
B2 | Dashboard | Valid User(s) | Only valid user(s) can access this module.
B3 | Dashboard | Valid User(s) | Only valid user(s) can access this module.
B4 | Dashboard | Valid User(s) | Only valid user(s) can access this module.
B5 | Dashboard | Valid User(s) | Only valid user(s) can access this module.
B6 | SPA | Valid User(s) | Only valid user(s) can access this module.
B7 | SPA | Valid User(s) | Only valid user(s) can access this module.
B8 | SPA | Valid User(s) | Only valid user(s) can access this module.
B9 | SPA | Valid User(s) | Only valid user(s) can access this module.
B10 | SPA | Valid User(s) | Only valid user(s) can access this module.
B11 | SPA | Valid User(s) | Only valid user(s) can access this module.
B12 | Budget Manager | Valid User(s) | Only valid user(s) can access this module.
B13 | Budget Manager | Valid User(s) | Only valid user(s) can access this module.
B14 | Budget Manager | Valid User(s) | Only valid user(s) can access this module.
B15 | Budget Manager | Valid User(s) | Only valid user(s) can access this module.
B16 | Master Admin | Valid User(s) | Only valid user(s) can access this module.
B17 | SPA Approver Mobile View | Valid User(s) | Only valid user(s) can access this module.

## RTM
REQUIREMENT TRACEABLE METRIC
Project Title
BR# | Requirement Description | Test Scenario ID | Test Case ID | Test Case Status
B1 | Verify removal of email trigger after successful login | TS_LN_01 | TC_LN_01_001
B2 | Verify Overall View export with correct UI display and CSV data | TS_DD_01 | TC_DD_01_001
B3 | Verify Watcher View export with correct UI and CSV data | TS_DD_02 | TC_DD_01_002
B4 | Verify Approver View export with correct UI and CSV data | TS_DD_03 | TC_DD_01_003
B5 | Verify Turnover Time (Days, Hours, Minutes) shown next to Completed status percentage | TS_DD_04 | TC_DD_01_004
B6 | Verify Rich Text Editor functionality in Summary of the Procurement field | TS_SA_01 | TC_SA_01_001
B7 | Verify all UI elements and actions in Additional Document Details section | TS_SA_02 | TC_SA_01_002
B8 | Verify UI fields, character limits and successful send action | TS_SA_03 | TC_SA_01_003
B9 | Verify Turnover Time visibility and value based on SPA status | TS_SA_04 | TC_SA_01_004
B10 | Verify document upload creates new SPA version and updates consolidated PDF | TS_SA_05 | TC_SA_01_005
B11 | Verify completed SPA PDF is password protected and file name is generated based on current date & time | TS_SA_06 | TC_SA_01_006
B12 | Verify Budget Manager screen, search by name/email and sort option | TS_BM_01 | TC_BM_01_001
B13 | Verify that adding a Budget Manager during SPA creation is reflected in Budget Manager tab list | TS_BM_02 | TC_BM_01_002
B14 | Verify Export All and Export Selected options | TS_BM_03 | TC_BM_01_003
B15 | Verify navigation between pages using pagination controls | TS_BM_04 | TC_BM_01_004
B16 | Verify Master Admin permissions and email notification exclusion | TS_MA_01 | TC_MA_01_001
B17 | Verify mobile responsiveness and approval functionality for Approvers | TS_SA_01 | TC_SA_01_001

## SPA
SYSTEM INTEGRATION TESTING (SIT)
Project Name:
Created By: | Bala Subra Maniyan S R
Creation Date:
Reviewed By:
Reviewed Date:
SL NO | TEST SCENARIO ID | SCREEN NAME | TEST SCENARIO DESCRIPTION | UI/FUNCTIONAL | TEST CASE ID | TEST CASE DESCRIPTION | TEST STEPS | TEST DATA | EXPECTED RESULT | Result | Comment
1 | TS_LN_01 | Login | Validate system does NOT send email notification on successful user login | UI/Functional | TC_LN_01_001 | Verify removal of email trigger after successful login | 1. Login to the application with valid user credentials 2. Verify user is logged in successfully and redirected to dashboard 3. Check user mailbox associated with the login account | NA | The user is logged in successfully without any UI error. No email notification is triggered or received upon successful login, and no background email job is executed for the login action. The login functionality operates normally and is not dependent on any email notification feature.
2 | TS_DD_01 | Dashboard | Validate UI elements and export functionality of Overall View dashboard with pie chart | UI/Functional | TC_DD_01_001 | Verify Overall View export with correct UI display and CSV data | 1. Navigate to Dashboard → Overall View 2. Verify presence of filters, pie chart, status list and Export Overall button 3. Apply filters 4. Verify pie chart updates correctly 5. Click Export Overall button 6. Download and open CSV file | NA | The Export button is visible and clickable. The pie chart and status counts are displayed correctly on the UI. The CSV file downloads successfully without any errors, and the exported CSV contains status-wise SPA counts that accurately match the data shown in the UI pie chart.
3 | TS_DD_02 | Dashboard | Validate UI elements and export functionality of Watcher View dashboard | UI/Functional | TC_DD_01_002 | Verify Watcher View export with correct UI and CSV data | 1. Navigate to Dashboard → Watcher View 2. Verify pie chart, status list and export icon visibility 3. Apply available filters 4. Validate pie chart status counts 5. Click Export icon 6. Open downloaded CSV | NA | The UI elements render properly, and the Export icon is enabled and accessible. The CSV file downloads without any errors, and the status and count values in the CSV accurately match the data displayed in the Watcher View pie chart.
4 | TS_DD_03 | Dashboard | Validate UI elements and export functionality of Approver View dashboard | UI/Functional | TC_DD_01_003 | Verify Approver View export with correct UI and CSV data | 1. Navigate to Dashboard → Approver View 2. Verify pie chart displays Pending and Approved status 3. Verify export icon visibility 4. Apply filters if available 5. Click Export icon 6. Open CSV file | NA | The pie chart loads correctly on the dashboard, and the Export icon is visible and clickable. The CSV file downloads successfully without any errors, and the Pending and Approved counts in the exported CSV accurately match the values displayed in the UI.
5 | TS_DD_04 | Dashboard | Validate Turnover Time is calculated and displayed correctly for Completed SPA status | UI/Functional | TC_DD_01_004 | Verify Turnover Time (Days, Hours, Minutes) shown next to Completed status percentage | 1. Navigate to Dashboard → Overall View 2. Verify pie chart and status list are displayed 3. Locate Completed status in status list 4. Verify Turnover Time is displayed next to Completion Percentage 5. Validate displayed Turnover Time format (Days, Hours, Minutes) 6. Cross-check calculation using SPA Created Date & SPA Completed Date | NA | Turnover Time is displayed only for the Completed status and is shown in Days, Hours, and Minutes format. The time is calculated from SPA Created to SPA Completed, and the displayed Turnover Time accurately matches the backend or system-calculated data.
6 | TS_SA_01 | SPA | Validate Text field is replaced with Rich Text Editor for “B. Summary of the Procurement” and supports all formatting options | UI/Functional | TC_SA_01_001 | Verify Rich Text Editor functionality in Summary of the Procurement field | 1. Navigate to SPA Module. 2. Click on Add SPA 3. Locate “B. Summary of the Procurement (e.g Background, Evaluation & Justification)” field 4. Verify the field is displayed as a Rich Text Editor (not a plain text box) 5. Enter text content 6. Add bullets and numbering 7. Insert a table 8. Add a hyperlink 9. Change font type, size, color, style (bold/italic/underline) and text alignment 10. Save SPA 11. Open the same SPA in Edit mode | NA | The Rich Text Editor is displayed in place of the standard text field. All toolbar options, including table insertion, bullets, numbering, hyperlink, text alignment, and font style, size, and color, are visible and fully functional. The formatted content is saved successfully, and all formatting is retained when the SPA is reopened in edit mode.
7 | TS_SA_02 | SPA | Validate visibility and functionality of Additional Document Details UI elements | UI/Functional | TC_SA_01_002 | Verify all UI elements and actions in Additional Document Details section | 1. Navigate to SPA Module. 2. Click on Add SPA 3. Fill all details 4. Navigate to Project Document Page 5. Scroll to Additional Document Details section 6. Verify info text “Please enter your document details” is visible 7. Verify Document Name field is displayed 8. Verify placeholder text “Enter the document name” is displayed 9. Verify Document Link field is displayed 10. Verify placeholder text “Enter the document link” is displayed 11. Verify Delete (trash) icon is visible 12. Click + Add Another option | NA | The “Please enter your document details” text is visible on the screen. The Document Name and Document Link fields are displayed correctly with the expected placeholder text. The Delete button is visible for each document entry, and clicking + Add Another successfully adds a new document entry row.
8 | TS_SA_03 | SPA | Validate Send Document popup works similar to email functionality | UI/Functional | TC_SA_01_003 | Verify UI fields, character limits and successful send action | 1. Navigate to SPA module 2. Open any SPA record in View mode 3. Click Action → Send 4. Verify Send Document popup is displayed 5. Verify presence of To, Cc, Bcc, Email Subject, Email Message fields 6. Enter valid email IDs in To, Cc and Bcc fields 7. Enter Email Subject within 998 characters 8. Enter Email Message within 5000 characters 9. Click Send button | NA | The Send popup UI matches standard email functionality, and all fields are visible and editable. Character limits are properly enforced, with the Subject field limited to 998 characters and the Message field limited to 5000 characters. Clicking Send successfully delivers the document, and the success message “Document Delivered Successfully” is displayed.
9 | TS_SA_04 | SPA | Validate Turnover Time is displayed only for Completed status and shown as “NA” for other statuses | UI/Functional | TC_SA_01_004 | Verify Turnover Time visibility and value based on SPA status | 1. Navigate to Dashboard → SPA Tab 2. Verify SPA list/status section is displayed 3. Locate SPA records with different statuses (Created, In Progress, Cancelled, Rejected, Expired, Completed) 4. Check Turnover Time column/value for Completed SPA 5. Check Turnover Time for all other statuses | NA | Turnover Time is displayed only for the Completed status, and the Completed SPA shows the Turnover Time in Days, Hours, and Minutes format. All other statuses display “NA – Not Applicable,” and no incorrect or partial time values are shown.
10 | TS_SA_05 | SPA | Validate SPA version creation and PDF consolidation when new document is added | UI/Functional | TC_SA_01_005 | Verify document upload creates new SPA version and updates consolidated PDF | 1. Navigate to SPA module and open an existing SPA 2. Click on SPA Versions tab 3. Verify existing uploaded documents are displayed with version numbers 4. Click Add button and upload a new PDF document 5. Save the SPA and Verify a new version number is created with updated timestamp 6. Expand the latest version and verify document name follows Project ID format 7. Click the eye icon for the latest version and Verify the PDF opens successfully 8. Validate PDF contains updated project information and uploaded documents 9. Verify all newly added PDFs are merged and stored in one consolidated PDF 10. Under Project Documents, click each document name | NA | The uploaded document is saved successfully, and a new SPA version is created with the correct version number and updated timestamp. The document name is displayed with the corresponding Project ID. Clicking the eye icon opens the correct PDF version, which contains the updated project details and uploaded documents. All PDFs are merged into one consolidated PDF, and each Project Document link opens the respective PDF successfully.
11 | TS_SA_06 | SPA | Validate password logic and dynamic file naming for completed SPA PDF | UI/Functional | TC_SA_01_006 | Verify completed SPA PDF is password protected and file name is generated based on current date & time | 1. Open a Completed SPA record 2. Click Actions → Download or View 3. Verify downloaded/opened file name format 4. Attempt to open the PDF 5. Enter incorrect password and verify access is denied 6. Enter correct password (Subsidiary/Division + Project ID) 7. Verify PDF opens successfully | NA | The Completed SPA PDF is password protected, and a password-required popup appears when attempting to open the file. Entering an incorrect password does not allow access to the PDF, while entering the correct password, which is a combination of Subsidiary/Division and Project ID.successfully opens the file. The password format strictly follows this defined rule. Additionally, the file name is generated dynamically in the format SPA_DDMMYYYY_HHMMSS.pdf instead of SPA-000123.pdf, and it accurately reflects the current date and time of download or view.
12 | TS_BM_01 | Budget Manager | Validate Budget Manager module visibility, search and sort functionality | UI/Functional | TC_BM_01_001 | Verify Budget Manager screen, search by name/email and sort option | 1. Veriy presence of Budget Manager Module 2. Click Budget Manager from left menu 3. Verify Budget Manager page loads successfully 4. Verify Search Budget Manager field is visible 5. Enter a user Name in search field 6. Clear and enter Email ID in search field 7. Click sort icon on Name and Email Id columns | NA | The Budget Manager module is visible on the screen, and the Search field is displayed properly. The user is able to search using both Name and Email ID, and the matching records are displayed correctly based on the entered criteria. The Sort icon functions as expected, sorting the data in ascending and descending order accordingly.
13 | TS_BM_02 | Budget Manager | Validate Budget Manager added during SPA creation appears in Budget Manager module list | UI/Functional | TC_BM_01_002 | Verify that adding a Budget Manager during SPA creation is reflected in Budget Manager tab list | 1. Navigate to SPA → Add SPA 2. Fill in required Project Information 3. In Budget Manager section, select/designate a new Budget Manager 4. Complete SPA creation and save 5. Navigate to Budget Manager module from left menu 6. Search for the newly added Budget Manager by Name or Email | NA | The Budget Manager is added successfully during SPA creation, and the newly added Budget Manager is visible in the Budget Manager tab list. The details such as Name and Email match exactly with the entered data, and no duplication or data mismatch occurs in the system.
14 | TS_BM_03 | Budget Manager | Validate export functionality for All and Selected records | UI/Functional | TC_BM_01_003 | Verify Export All and Export Selected options | 1. Navigate to Budget Manager module 2. Verify Export button is visible 3. Click Export without selecting any checkbox 4. Download the file 5. Select one or more records using checkbox 6. Click Export again 7. Download the file | NA | The Export button is visible and enabled. When no records are selected, all records are downloaded in .csv / Excel format. When specific records are selected, only the selected records are downloaded. The exported data accurately matches the records displayed in the UI list.
15 | TS_BM_04 | Budget Manager | Validate pagination functionality in Budget Manager module | UI/Functional | TC_BM_01_004 | Verify navigation between pages using pagination controls | 1. Navigate to Budget Manager module 2. Verify pagination controls are visible at bottom 3. Click on page number (2, 3, Next, Previous) 4. Navigate back to first page | NA | Pagination controls are visible on the screen, and the user can navigate between pages successfully using the available controls. The correct records are displayed on each respective page, and the active page is clearly highlighted to indicate the current selection.
16 | TS_MA_01 | Master Admin | Validate Master Admin role has Admin-level access with restricted email notification and APC member handling behavior | UI/Functional | TC_MA_01_001 | Verify Master Admin permissions and email notification exclusion | 1. Login to application as Master Admin user 2. Navigate through SPA modules and verify access is same as Admin (Dashboard, SPA, Approvals, etc.) 3. Complete an SPA 4. Verify email notifications triggered for other applicable roles 5. Check Master Admin mailbox for SPA Completion email 6. Navigate to approvers section 7. Attempt to edit approvers details | NA | Master Admin has the same access rights as Admin across all SPA modules, and the SPA completion workflow executes successfully. Email notifications are sent to other configured roles as per the standard process; however, the Master Admin does not receive the SPA completion email. Additionally, the Master Admin allowed to edit approver details,
17 | TS_SA_01 | SPA Approver Mobile View | Validate SPA Portal is mobile responsive and fully functional for Approver role | UI/Functional | TC_SA_01_001 | Verify mobile responsiveness and approval functionality for Approvers | 1. Open SPA Portal in mobile browser 2. Login as Approver 3. Verify dashboard layout adjusts properly to mobile screen 4. Click on SPA and verify navigation works 5. Click on SPA Approvals and verify page loads without layout issues 6. Click on SPA Watchers and verify proper display 7. Verify the functionality of Approve and Reject functionality in SPA Approvers module 8. Confirm action and verify status update | NA | The dashboard adjusts correctly to mobile resolution, and the sidebar or menu items are visible and properly aligned. There are no UI overlaps. All modules navigate correctly without layout distortion. The Approve and Reject buttons are accessible and fully functional on mobile devices, and the status updates successfully after confirmation.

## MAISP (05)
SECURITY TESTING (MAISP)
Project Name: | <Name of Project>
Created By:
Creation Date:
Reviewed By:
Reviewed Date:
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Data | Expected Result | Test Results | Comment(s)
TS_MAISP_001 | Login to system, application or server | TC_MAISP_SAS_001 | Access to system, application or server the first time | Main page displayed for the respective system, application or server | Username: registered username Password: default password | User(s) successfully logs-into the system, application or server using the registered username and default password.
TS_MAISP_002 | To change password | TC_MAISP_CP_001 | To ensure user(s) changes his / her password that contains a minimum of eight (08) character & contains uppercase (ABC), lowercase (abc), numbers (0,1,2) and special characters (#$@) | N/A | N/A | User(s) successfully changes his / her password that contains a minimum of eight (08) character and contains uppercase (ABC), lowercase (abc), numbers (0,1,2) and special characters (#$@).
TS_MAISP_003 | To notify expiry of current password | TC_MAISP_EP_001 | Message box or prompt alert to notify user(s) that change of password occurs every 45 days. | N/A | Username: registered username Password: current password Message to user(s): Your password will expire in xx days. Please change your password. | Change of password to occur every 45 days
TS_MAISP_004 | To verify 5 unsuccessful attempts to enter a password | TC_MAISP_ATT_001 | 5 unsuccessful attempts to enter a password | Login using invalid Password | Invalid Password | After 5 unsuccessful attempts to enter a password, the said user id must be suspended until reset by administrator . Message box “Username has been blocked. Please contact the Administrator to Reset ” is displayed.
TS_MAISP_005 | To verify account lockout duration: 30 min | TC_MAISP_LK_001 | Lock account which ideal more than 30 minutes | Leave the application/ server untouchable for 30 minutes | N/A | Application/ Server locked
Other Comment(s) :
[9 empty] | Application Name | Total Payable | Payable Date | Monthly Payable | Month Pending
[9 empty] | InstaMoney | 5562 | 1st | 1854 | 3 Month
[9 empty] | Moneyview | 5910 | 7th | 985 | 6 Month
[9 empty] | Chimay | 6966 | 17th | 3646 | 2 Month
[9 empty] | Ring | 5624 | 17th | 804 | 7 Month
[9 empty] | Branch | 15023 | 19th | 1252 | 12 Month
[9 empty] | Kreditbee | 1808 | 23rd | 1808 | 1 Month
[9 empty] | Kisskit | 11755 | 28th | 1306 | 9 Month
[9 empty] | Application Name | Total Payable | Payable Date | Monthly Payable | Month Pending
[9 empty] | InstaMoney | 5562 | 1st | 1854 | 3 Month
[9 empty] | Chimay | 6966 | 17th | 3646 | 2 Month
[9 empty] | Kreditbee | 1808 | 23rd | 1808 | 1 Month

## Overall Results
No. | Test Results | Date
1 | Pass
2 | Pass with Condition
3 | Fail
4 | KIV
5 | N/A
6 | Other Comment(s)
7 | Future Enhancement(s)
Total Test Case(s):
To Test:
To Re-Test:
% Passed: